| Responsibility | PI / Dept | Dean / Director | OSP/ VT |
| --- | --- | --- | --- |
| Proposal Preparation and Submission |  |  |  |
| Reviews requests for proposals for technical requirements | X |  |  |
| Reviews requests for proposals for institutional compliance |  |  | X |
| Prepares Technical Proposal | X |  |  |
| Assures proposed project is appropriate and in-line with departmental and institutional mission | X | X |  |
| Assures proposed project has qualified personnel and adequate space | X |  |  |
| Develops initial budget draft to accomplish proposed scope of work | X |  |  |
| Reviews budget for appropriate salaries, fringes, tuition, indirect, and escalations |  |  | X |
| Requests and documents approval for cost sharing as required | X |  |  |
| Approves and provides documentation to OSP for cost sharing approval |  | X |  |
| Reviews and approves required and voluntary cost sharing |  |  | X |
| Works with the Purchasing Office to develop Small Business/Minority Subcontracting Plan | X |  |  |
| Submits Small Business/Minority Subcontracting Plan |  |  | X |
| Prepares final version of proposal as required by the sponsor | X |  |  |
| Completes Proposal Approval Form and as appropriate Forms A, B, or C and routes all forms for signatures | X |  |  |
| Provides proposal to OSP 48 hours in advance of sponsor deadline | X |  |  |
| Approves proposal and serves as signature authority |  |  | X |
| Copies and mails proposals as dictated by the Proposal Approval Form |  |  | X |
| Negotiates material transfer and confidentiality agreements |  |  | X |
| Negotiates teaming agreements |  |  | X |
| Maintains proposal pending files and database |  |  | X |
| Regulatory Compliance |  |  |  |
| Approves project principal investigator status |  | X |  |
| Approves research faculty as PI status |  |  | X |
| Prepares and submits protocols for research involving human subjects, animal use, and biosafety hazards | X |  |  |
| Ensures investigators are submitting protocols to appropriate compliance committee | X |  |  |
| Assures and provides documentation of certifications and representations to sponsor |  |  | X |
| Assures compliance with federal regulations regarding financial disclosure of potential conflicts of interest |  |  | X |
| Serves as the Industrial Security Office |  |  | X |
| Maintains security clearances for faculty & staff and is responsible for the receipt and the safe guarding of classified material |  |  | X |

| Responsibility | PI / Dept | Dean / Director | OSP / VT |
| --- | --- | --- | --- |
| Award Negotiation and Establishment |  |  |  |
| Accepts awards on behalf of the Virginia Tech Board of Visitors |  |  | X |
| Requests Letter of Guarantees (LOGs) in advance of official award | X |  |  |
| Reviews and approves LOGs in advance of official award |  | X |  |
| Negotiates award terms and conditions (publication restrictions, indemnification, intellectual property, governing law, payment terms, financial reporting requirements, and intellectual property) |  |  | X |
| Agrees to all terms and conditions as they relate to performance clauses (frequency of technical reports, special professional staff hourly reporting, deliverables, and conditions of termination) | X |  |  |
| Establishes award funds in accordance with award documentation |  |  | X |
| Initiates subawards | X |  |  |
| Negotiates and administers all subawards |  |  | X |
| Ensures subawardee is in compliance with A-133 |  |  | X |
| Maintains award database |  |  | X |
| Managing the Award |  |  |  |
| Initiates and encumbers personnel transactions | X |  |  |
| Assures appropriateness, reasonableness and allowability of expenditures | X |  |  |
| Provides oversight of sponsored project administration including the review of cost transfers and effort reporting | X | X |  |
| Reviews, tracks, and reports cost sharing efforts to sponsor |  |  | X |
| Reviews expenditures in restricted budget categories |  |  | X |
| Reviews and certifies personnel activity reports | X |  |  |
| Manages the personnel activity reporting system |  |  | X |
| Initiates requests for re-budgeting and cost transfers | X |  |  |
| Approves substantive modifications and re-budgeting |  | X |  |
| Reviews cost transfers and approves if transfer is > 90 days old |  |  | X |
| Requests no-cost time extensions | X |  |  |
| Reviews and approves requests for no-cost time extensions |  |  | X |
| Approves payment of subawardee invoices | X |  |  |
| Assures timely resolution of fund overdrafts |  | X |  |
| Revenue collection (invoicing, letter of credit drawdowns, wire xfers, etc) |  |  | X |
| Reconciles any revenue shortfalls |  |  | X |
| Reporting and Award Close-out |  |  |  |
| Prepares technical reports and provides other deliverables as required | X |  |  |
| Documents cost sharing funds as required | X |  |  |
| Prepares and submits to sponsor financial reports and final invoices as required |  |  | X |
| Participates in negotiations when technical reports are incomplete and deliverables are unacceptable to sponsor |  | X |  |
| Responds to close-out questionnaire | X |  |  |
| Files appropriate close-out documents |  |  | X |