## Post Awd Actng
POST AWARD ACCOUNTING PROJECT CLOSEOUT CHECKLIST
Project # (PeopleSoft Project ID)
PI Name
GEMS#/InfoEd#
Sponsor Award #
Project End Date
Project Close Cycle/Due date for final deliverables (days after end date) |  | 60
Estimated Closeout Due Date
# | Suggested Process Step | Date Complete | Comments | Initial
1 | Award Closeout Preparation
1.1 | Post Award Accounting confirms with OSR Grants & Contracts Coordinator and Department administrator that project is due to be closed.
1.2 | Check that project and activity status are "E-Ended - Past Official End Date"
2 | Prepare FFR/Financial report
2.1 | Run Award Closeout Queries:
2.1.1 | COH_GM_OPEN_FA_ON_AWD_CLOSE
2.1.2 | COH_PCGRT_PCOTR_OPEN_PO_BY_PRJ - PCGRT
2.1.3 | COH_GM_OPEN_REQS_ON_AWD_CLOSE
2.1.4 | COH_AP_RCPT_ACCR
2.1.5 | COH_GM_OPEN_JRNLS_ON_AWD_CLOSE
2.1.6 | COH_GM_VCHRS_POSTED_UNPAID_LOC
2.2 | Prepare FFR/financial report
2.2.1 | Run RER (Research Expenditure Report)
2.2.2 | Run Labor Distribution Reports (if needed)
2.2.3 | Review Open AR; if yes, push collection efforts
2.2.4 | Review for any deferred revenue; if yes, can it apply against open AR or agree to contract for payback terms
2.2.5 | Review for any unbilled AR
2.3 | Send preliminary FFR/financial report to Department for review
3 | Capital Equipment
3.1 | Alert Fixed Assets Accountant to notify Research Finance of any capital equipment purchase closeouts
4 | Funds (Overspent/Underspent)
Overspent Funds
4.1 | Confirm that balance from FFR/financial report shows negative balance
4.2 | Confirm that cost transfer has been prepared and posted
4.3 | If deficit is within de minimis threshold, prepare journal entry to resolve the deficit to the appropriate chart string
Underspent Funds
4.4 | Confirm that balance from FFR/financial report shows underspent funds
4.5 | Confirm that balance will be returned, or if the surplus is within de minimis threshold (on Fixed Price contracts), prepare journal entry to transfer the surplus to the appropriate chart string or submit a check request to return unspent funds to the sponsor
5 | Final Approval of FFR/Financial Report
5.1 | Receive approved FFR/financial report back from Department
5.2 | Review department adjustments with supporting documentation
5.3 | Receive and process final invoice request
5.4 | Run query to ensure that all transactions have been posted
5.5 | Confirm that F&A calculations are correct and prepare adjustments if needed
5.6 | Confirm for CIRM/DOD awards the DD882/etc. Patent/Invention form is completed
6 | Review and approve FFR/Financial Report Worksheet
6.1 | Run RER for completed award; confirm that amount in RER matches amount submitted in FFR/financial report
6.2 | Run RER to confirm that final, cumulative invoice amounts match what was billed
6.3 | Confirm that FFR/financial report amount matches draw down amount
6.4 | Submit FFR/financial report
6.5 | Save FFR/financial report confirmation and file electronically in shared drive
6.6 | Upload submitted FFR/financial report in InfoEd
7 | Final Award Closeout Post Submission of FFR/Financial Report
7.1 | Verify: Budget=Expense=Revenue
7.1.1 | Apply any remaining payments/collections items
7.2 | Notify Corporate Accounting to inactivate Combo Code and Combo Edits
7.3 | Receive all closeout checklists and attach to award in PS
7.4 | Cancel bill plan for Fixed Fee awards
7.5 | Update PeopleSoft Project to "I-Inactive"
7.6 | Scan and save all hard copy documents to electronic PI/Project folder
8 | Closeout Complete
8.1 | Print the completed checklist, sign, and forward to OSR for archival with the award.
By signing this document, the Accountant acknowledge that he/she has reviewed and completed all necessary steps to complete the financial closeout of the project.
Signature / Date
rev. 7/30/18
Note: if deliverables are not all due the same day, deadlines will need to be manually adjusted.
Note on C9: This cell is a calculated date. Change with caution!