## Department
DEPARTMENT PROJECT CLOSEOUT CHECKLIST
Project # (PeopleSoft Project ID)
PI Name
GEMS#/InfoEd#
Sponsor Award #
Project End Date
Project Close Cycle/Due date for final deliverables (days after end date) |  | 60
Estimated Closeout Due Date
# | Suggested Process Step | Date Complete | Comments | Initial
1 | Award Closeout Preparation
1.1 | Department administrator confirms with OSR Grants & Contracts Coordinator and Post Award Accounting that project is due to be closed.
1.2 | Check RAFT for open PO's, Reqs, encumbrances, etc. and proceed to zero, release, or resolve
2 | Subcontractors
2.1 | Notify subrecipients of upcoming deadline date and collect outstanding invoices
2.2 | Send subcontractor monitoring documentation from Dept/PI to OSR (if applicable)
2.3 | Ensure all invoices are submitted for vouchering to issue payment
2.4 | Confirm all invoices from subcontractors have been posted
3 | Project Review
3.1 | Reconcile line item expenses and budget
3.2 | Review Facilities & Administrative (F&A) charges, and notify PAA of any discrepancies
4 | Final Invoices
4.1 | Complete Invoice Request Form (if applicable)
5 | Payroll
5.1 | Run Labor Distribution Report
5.2 | Confirm fringe rate/costs
5.3 | Update API grant tracking for all employees currently charging salary to the ending project, in the pay period that the project ended.
5.4 | Submit any Labor Cost Transfers needed
5.5 | Ensure outstanding effort reports are certified.
6 | Review FFR
6.1 | Review preliminary FFR Worksheet
6.2 | Request adjustments with supporting documentation as needed
6.3 | Obtain PI approval (on paper and scan, or via email)
6.4 | Send to Post Award Accounting
7 | Residual Funds
7.1 | If residual funds are to be transferred, complete and submit a Request For Retention of Residual Funds form to Research Finance.
7.2 | If funds are to be returned to sponsor, request Post Award Accounting to submit a check request and letter to sponsor after final FFR is approved.
7.3 | Verify that payments have been posted
8 | Overspent Funds (Fund Deficit)
8.1 | Prepare cost transfer to zero out deficits greater than $100.
8.2 | Confirm that cost transfer has been posted
9 | Closeout Complete
9.1 | Print the completed checklist, obtain the PI’s signature, sign and forward to OSR for archival with the award.
Chartstring for late charges after project has been closed:
By signing this document, the PI and department administrator acknowledge that he/she has reviewed and completed all necessary steps to complete the departmental closeout of the project. Any late charges occurring after the project has been closed will be posted to the chartstring noted above, regardless of allowability to charge the project in normal circumstances.
PI Signature / Date
Dept Admin Signature / Date
Detailed Department Instructions
1 | Award Closeout Preparation
If the award is assigned a different activity for each budget period, confirm all previous year project balances are zero and the activities have been inactivated in PeopleSoft.
Complete review of all general ledger transactions via “COH_GL_ACCOUNT_DETAIL query, and process necessary adjustments to be posted to general ledger.
Confirm the authorized award amount in the PeopleSoft budget agrees with the approved budget per an award Notice of Award and all subsequent amendments and modifications.
Take action to release (liquidate), change, or cancel any open purchase orders in PeopleSoft to address remaining encumbrances.
Transfer unallowable expenses, if any.
Transfer or justify transactions outside the award period of performance.
2 | Subcontractors
Ensure correct account numbers are used: • 66920x: for the first $25,000 of sub-award expense to assess overhead • 66930x: for sub-award expenses in excess of $25,000 to be exempt from overhead
3 | Project Review
If restricted funding exists, confirm that expenses are tracked separately and indicate the unobligated balance of each restricted funding.
If the award requires mandatory cost share or has voluntary committed cost share, provide a cost share contribution report and supporting documents, as applicable.
5 | Payroll
If the award is subject to a salary cap, transfer salaries in excess of the salary cap amount.
If the award is subject to e-verify, transfer salaries not in compliance with e-verify requirement.
7 | Residual Funds
If the award is Fixed Rate/Fixed Price and has an unexpended balance, provide assurance, explanation, and endorsement in accordance with the “Residual funds on Sponsored Projects” policy.
Note: if deliverables are not all due the same day, deadlines will need to be manually adjusted.
Note on C9: This cell is a calculated date. Change with caution!