## Project Closeout Checklist
| Project: Fund: |  | End Date:
Status | Activity | Lead | Start | End | Notes
| INITIATE PROJECT CLOSEOUT |  |  |  |  | PM=
Not started | Research funder requirements, adapt below as needed | G&C | -125 | -120 |  | G&C= | Samantha Levin
Not started | Adapt list below as needed | PM, with G&C | -120 | -120 |  | Accounting= | Sarah Howgate
| PROGRAMMATIC |  |  |  |  | Communications=
Not started | Conduct Project Closeout Meeting three months before close out | PM, with G&C & Accounting | -90 | -90 |  | AD=
Not started | Go over workplan to ensure deliverables are met in a timely manner | PM | -45 | -45
Not started | Draft final narrative report | PM | 1900-01-29 | 1900-03-30
Not started | Consider conducting exit interviews with project stakeholders (subs, participants, staff) | PM | -60 | 0
Not started | Close all project sub-grants or contracts in advance of final report prep | G&C | -90 | -30
Not started | Conduct a Project Closeout presentation/Conduct Project Debrief Meeting within a month of EOP | PM | -15 | 1900-03-30
Not started | Recognition of project and project team (ex. event, email, presentation) | PM/AD | -7 | 0
PERSONNEL
Not started | Conduct staff exit interviews | HR | -15 | 0
Not started | Manager speaks with exiting staff about professional interests and potential fits elsewhere in the College | PM/AD | -30 | 0
Not started | Update default allocations for staff that are staying with the College | PM/AD | 0 | 1900-01-06
FINANCIAL
Not started | Conduct budget closeout planning meeting (6 and 3 months out) | G&C | -180 | -90 | with PM and Accounting, review entire GL, staff time and effort, and projections
Not started | Plan for and monitor closeout costs | PM | -180 | 1900-01-29
Not started | Coordinate budget closeout with other project budgets | AD | -60 | 1900-02-28
Not started | Coordinate with Accounting on end of FY indirect costs | G&C | -45 | 1900-03-30
Not started | Inform Finance of fund closure/Freeze Fund | G&C | 1900-01-29 | 1900-01-29
Not started | Consult with Accounting on what to do with remaining budget balance | AD | -60 | 1900-02-13
Not started | Determine what final invoices are coming due | PM | -60 | -30
Not started | Inform vendors where to direct final invoices and by what date | PM | -60 | -30
Not started | Direct staff to submit reimbursements and by what date | PM | -60 | -30
Not started | Send Subaward Close Out Letters | G&C | -60 | -30
Not started | Submit final list of invoices and payment plan to Finance noting accruals needed | PM | -30 | -30
Not started | Submit any outstanding invoices to funder, if applicable | Accounting | 1900-01-29 | 1900-01-29
Not started | Drawdown remaing expenses/Return unused advanced funds | Accounting | 1900-01-29 | 1900-01-29
Not started | Prepare final financial report | Accounting | 1900-02-28 | 1900-02-28
ADMINISTRATIVE
Not started | Review file retention requirements | G&C | -120 | -120
Not started | Review grant folder to ensure completeness | G&C | -30 | 0
Not started | Complete Invention Paperwork | G&C | 0 | 0
Not started | Complete Inventory Paperowrk | G&C | 0 | 0
Not started | Complete Publications Paperwork | PM | 0 | 0
Not started | Submit final narrative and financial report to donor | G&C | -15 | 1900-03-30
Not started | Move locally stored data (or data in inboxes) to shared drive | PM | -30 | 0
Not started | Scan relevant paper files, destroy all paper files | PM | -30 | 0
Not started | Move folder on share drive to Closed Projects | G&C | -30 | 0
COMMUNICATIONS
Not started | Ensure that all press/journals are in fund folder | G&C | -30 | 0
Not started | Create close out paragraph for next BOR report | PM | -30 | 0
Not started | Draft project close email with results and appreciation to go out to division | AD | -15 | 0
Not started | Inform key contacts and stakeholders of EOP date 2 months in advance | PM | -30 | 0
Not started | Send thank you notes to key contacts | PM | -15 | 0
Not started | Submit website updates as appropriate | PM | -15 | 0
Not started | Publicize results of program activities | Communications | -45 | 1900-01-29
Formulas:
End = [Start]
End = [End, row above]

## Sheet1
Not started
In Progress
Completed
Not applicable