## JUL2022
[9 empty] | PAGE | 1 | OF PAGES | 1
| National Aeronautics and Space Administration | Monthly Contractor Financial Management Report |  |  |  |  | Form Approved O.M.B. No. 2700-0003 |  | 2. REPORT FOR MONTH ENDING AND NUMBER OF WORKING DAYS
July 31, 2022 (19)
TO: |  |  |  | FROM: |  |  |  |  | 3. CONTRACT VALUE
FUNDING AGENCY INFO |  |  |  | INSTITUTIONAL INFO |  |  |  |  | a. COST |  | b. FEE
[9 empty] | 160000 |  | $
1. DESCRIPTION OF CONTRACT | a. TYPE |  |  | b. CONTRACT NO. AND LATEST DEFINITIZED MODIFICATION NO. |  |  |  |  | 4. FUND LIMITATION
| Cost No-Fee / Cost Reimbursable | [7 empty] | 160000
| c. SCOPE OF WORK |  |  | d. AUTHORIZED CONTRACTOR REPRESENTATIVE (Signature) |  |  |  | DATE | 5. BILLING
| PROJECT TITLE | [6 empty] | 2022-08-10 | a. INVOICE AMTS. BILLED $ |  | b. TOTAL PYTS. REC'D. $
[9 empty] | 116976.56 |  | 95833.15
6. REPORTING CATEGORY |  | 7. COST INCURRED/HOURS WORKED |  |  |  | 8. ESTIMATED COST/HOURS TO COMPLETE |  |  | 9. ESTIMATED FINAL COST/HOURS |  |  | 10. UNFILLED ORDERS OUTSTANDING
|  | DURING MONTH |  | CUM. TO DATE |  | DETAIL |  | BALANCE OF CONTRACT c.
|  | ACTUAL a. | PLANNED | ACTUAL | PLANNED |  |  |  | CONTRACTOR ESTIMATE a. | CONTRACT VALUE b.
[6 empty] | 2022-08-22 | 2022-09-22
|  | a. | b. | c. | d. | a. | b.
Direct Labor Hours
Position Title, Name (EE Classification) 1 |  | 72 | 108 | 895.18 | 1062.03 | 128.95 | 128.95 | 0 | 1153.08 | 1147.4 |  | 0
Position Title, Name (EE Classification) 2 |  | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 120 | 0
Direct Labor Hours Total |  | 72 | 108 | 1015.18 | 1062.03 | 128.95 | 128.95 | 0 | 1273.08 | 1147.4 |  | 0
OT Labor Hours
Position Title, Name (EE Classification) 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Position Title, Name (EE Classification) 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Direct Labor Hours Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Direct Labor Dollars
Position Title, Name (EE Classification) 1 |  | 4721.61 | 7211.48 | 59357.79 | 73549.48 | 8456.46 | 8456.46 | 0 | 76270.71 | 79871 |  | 0
Position Title, Name (EE Classification) 2 |  | 0 | 0 | 3975 | 0 | 0 | 0 | 0 | 3975 | 0
Direct Labor Dollars Total |  | 4721.61 | 7211.48 | 63332.79 | 73549.48 | 8456.46 | 8456.46 | 0 | 80245.71 | 79871 |  | 0
OT Labor Dollars
Position Title, Name (EE Classification) 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Position Title, Name (EE Classification) 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
OT Labor Dollars Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Labor O/H Dollars
EE Classification 30.4% (FY21) |  | 0 | 0 | 5284.67 | 12033 | 0 | 0 | 0 | 5284.67 | 12033 |  | 0
EE Classification 28.1% (FY22) |  | 0 | 0 | 10472.09 | 7518 | 0 | 0 | 0 | 10472.09 | 11322
EE Classification 28.3% (FY23) |  | 1336.21 | 2040.85 | 1336.21 | 2040.85 | 2393.1782 | 2393.1782 | 0 | 6122.5664 | 0
EE Classification (<12 mos) 27.7% (FY21) |  | 0 | 0 | 1101.06 | 0 | 0 | 0 | 0 | 1101.06 | 0
Labor O/H Dollars Total |  | 1336.21 | 2040.85 | 18194.03 | 21591.85 | 2393.1782 | 2393.1782 | 0 | 22980.3864 | 23355 | 0 | 0
Total Labor Dollars |  | 6057.82 | 9252.33 | 81526.82 | 95141.33 | 10849.6382 | 10849.6382 | 0 | 103226.0964 | 103226 | 0 | 0
ODCs
Travel |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Equipment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Materials |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subcontracts |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Miscellaneous |  | 0 | 0 | -0.3 | 0 | 0 | 0 | 0 | -0.3 | 0 | 0 | 0
Utilities |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total ODCs |  | 0 | 0 | -0.3 | 0 | 0 | 0 | 0 | -0.3 | 0 |  | 0
Subtotal (Labor+ODCs)) |  | 6057.82 | 9252.33 | 81526.52 | 95141.33 | 10849.6382 | 10849.6382 | 0 | 103225.7964 | 103226 |  | 0
G&A Expense (55.0%) |  | 3331.79 | 5089 | 44839.59 | 52327.95 | 5967.3 | 5967.31 | 0 | 56774.2 | 56774 |  | 0
G&A Check |  | 3331.801 | 5088.7815 | 44839.586 | 52327.7315 | 5967.301 | 5967.301 | 0 | 56774.188 | 56774.3 |  | 0
TOTAL COSTS |  | 9389.61 | 14341.33 | 126366.11 | 147469.28 | 16816.9382 | 16816.9482 | 0 | 159999.9964 | 160000 |  | 0
Baseline Plan Identification (Col. 7b & 7d): Revision No. | [5 empty] | , Dated
NASA FORM 533M AUG 96 PREVIOUS EDITIONS ARE OBSOLETE. | [10 empty] | RCS 1ØPUBLØØ417