## ORNL Checklist
DOE Genesis Mission Phase I
| Submission Deadline in Grants.gov | 2026-04-28
| Final proposal documents to UTK | 2026-04-20
| Title | Pressure-to-Action Digital Twin for Subsurface Fractured Reservoirs: Safe Automation Under Uncertainty
| Performance Period | 7/1/26 - 3/31/27
Collaborative Budget Total
| Portal | grants.gov
General Formatting
| Font | 11 pt
| Margins | 1"
| Document Type | Page Limit | Primary Responsibility | File Type | Notes
1 | SF424 Cover | n/a | ORNL | Form | p. 55 and 62
2 | R&R Other Project Info | n/a | ORNL | Form | p. 64
2.a. | Project Summary/Abstract | 1 | UTK | received from lead. Field 7 | p. 64-65
2.b. | Title Page |  | UTK will provide to ORNL by 4/28 | Combined PDF provided from lead institution Attach in Field 8 of the Research and Related Other Project Information Form | p. 65
2.c. | Project Narrative | 5 |  |  | pp. 65-69
2.d. | Appendix 1: References | n/a |  |  | p. 69
2.e. | Appendix 2: Facilities & Other Resources | 0.5 |  |  | p. 70
2.f. | Appendix 3: Equipment | 0.5 |  |  | p. 70
2.g. | Appendix 4: Data Management & Sharing Plan | n/a |  |  | Not required at submission pp. 70-71
2.h. | Appendix 5: Synergistic Activities | 1 |  |  | optional p. 71
2.i. | Appendix 6: Transparency of Foreign Connections | n/a |  |  | template available pp. 71-72
2.j. | Appendix 7: Other Attachments |  |  |  | p. 72
2.j.i. | Letters of Commitment | 1 |  |  | required from partner institution p. 61
2.j.ii | Letters of Collaboration or Access |  | if needed ORNL will prepare and send to UTK. |  | conditionally required from institutions providing access to data, models, software, equipment and/or facilities; pp. 61-62
2.k. | Identification of Merit Reviewer Conflicts | n/a | ORNL | Excel | attach to field 12; pp. 55, 75, 102-103 https://science.osti.gov/-/media/grants/excel/Collaborator_Template.xlsx
2.l. | Senior personnel/partner inst/budget table | n/a | UTK | Excel | Lead Institution only; Field 12
3 | R&R Senior/Key Person Profile | n/a | ORNL | Form | p. 73; complete before budget form to prepopulate budget; include consultants if substantive involvement; credential field "PAMS" username, if known
3.a. | Bio sketches with ORCID ID | SciENcv | ORNL | PDF | p. 100-101; SciENcv
3.b. | Current & Pending support | SciENcv | ORNL | PDF | pp. 103-104; SciENcv
4 | R&R Budget Form | n/a | ORNL | Form | p. 55 and 73; your institution budget only; include travel to two Genesis meetings and to meet with collaborators
4.a. | Budget Justification | n/a | ORNL | PDF | pp. 73-74; 106-110 Provide the details of all personnel (key or other) who will be working on the award, regardless of their source(s) of compensation. Explain their source(s) of compensation if it is not from this award. Include the indirect cost rate agreement as a part of the budget justification.
6 | R&R Project/Performance Site | n/a | ORNL | Form | p. 55+75
7 | SF-LLL | n/a | ORNL | PDF | p. 75